## Planning
Planning Chart - Biereforce3
Task | Responsible | Priority | Progress (0-100) | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19
Brainstorming | All | High | 100 | bar: 2021-04-01 to 2021-04-02
Planning | All | High | 100 | bar: 2021-04-02
Create GIT structure in github | Gabriela | High | 100 | bar: 2021-04-03 to 2021-04-06
Cahier des Charges | Benjamin/Olivier | High | 100 | bar: 2021-04-02; 2021-04-06 to 2021-04-09
SWOT Analysis | Benjamin/Matthieu | Medium | 100 | bar: 2021-04-06
Personas | Benjamin | High | 100 | bar: 2021-04-06
Impact Mapping | Gabriela | High | 100 | bar: 2021-04-01 to 2021-04-02; 2021-04-06
Validation cahier des charges | All | High | 100 | bar: 2021-04-07
Review and finalize cahier des charges | All | High | 100 | bar: 2021-04-08
Define functionalities | All | High | 100 | bar: 2021-04-02
Charte Graphique | Matthieu | High | 100 | bar: 2021-04-06
Logo | Matthieu | High | 100 | bar: 2021-04-06
Wireframe | Gabriela | High | 100 | bar: 2021-04-06 to 2021-04-07
Define Technologies | All | High | 100 | bar: 2021-04-02
Search and select API | Olivier | High | 100 | bar: 2021-04-06
Install Software | All | High | 100
Research and select hosting | Olivier | High | 100 | bar: 2021-04-08 to 2021-04-09
Design data structure | Gabriela/Olivier | High | 100 | bar: 2021-04-06 to 2021-04-07
Front end development | Matthieu/Benjamin | High | 100 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
Page Main - Nav | Matthieu |  | 100 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
Javascript animations | Matthieu |  | 100 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
Page Event | Matthieu |  | 100 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
Page Login | Benjamin |  | 100 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
Responsive Design | Benjamin/Matthieu |  | 100 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
Texts and images | Matthieu/Benjamin |  | 100 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
SEO | Matthieu/Benjamin | High | 100 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
Back end development | Olivier/Gabriela | High | 100 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
CRUD - Users | Gabriela |  | 95 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
Upload User Images | Gabriela/Olivier |  | 80 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
CRUD - Evenements | Gabriela |  | 100 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
CRUD - Boites | Gabriela |  | 100 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
Implement google mailer for contact | Gabriela |  | 100 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
API - Online Payment | Gabriela/Olivier |  | 80 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
API - Connect with Google and Facebook | Olivier |  | 80 | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
Implement Cookies and GDPR | Gabriela | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
Integration Backend/Frontend | All | bar: 2021-04-07 to 2021-04-09; 2021-04-12 to 2021-04-15
Test and recette (Qualification) | All | High | bar: 2021-04-12 to 2021-04-14
Deployment | Olivier | High | bar: 2021-04-12 to 2021-04-15
Presentation PPT | All | High | bar: 2021-04-12 to 2021-04-16
Recherche implementation de RGPD et cookies | Olivier | High | bar: 2021-04-06 to 2021-04-08

## Hoja3
ID | WeekOf | Drink | Votes
1 | 2021-04-06 | Daikiri
2 | 2021-04-06 | Margarita
3 | 2021-04-12 | Tequila
4 | 2021-04-12 | Pisco Sour

## Priorités du jour
2021-04-06 | 2021-04-07
| Create GIT structure in github | Gabriela
| Cahier des Charges | Benjamin
| Personas | Benjamin
| Search and select API | Olivier
| Design data structure | Gabriela
| Recherche implementation de RGPD et cookies | Olivier
| Point d'etape RGPD | Olivier
| Implementation RGPD | Olivier

## Options
High
Medium
Low